| PrismRx Hackathon Sprint Plan Innovation Hacks 2026 ¦ Anton RX Track ¦ Medical Benefit Drug Policy Tracker | Build Executable coverage intelligence engine Core users Analyst + access coordinator Integrations Auth0 + ElevenLabs Demo posture Public docs + synthetic cases |
| --- | --- |

PrismRx turns fragmented medical-benefit drug policies into a searchable, comparable, and explainable workspace. The MVP focuses on public payer policy documents and synthetic patient scenarios so the team can demo real access intelligence without touching PHI.

| Normalize Convert payer PDFs and policy pages into structured Policy DNA objects. | Simulate Show approval blockers and the fastest approvable path for a case. | Explain Surface semantic policy changes, evidence, and next-best action. |
| --- | --- | --- |

| Winning wedge | Do not build a PDF chatbot. Build a policy decision layer that can compare coverage, surface blockers, and replay change impact. |
| --- | --- |
| Must ship | Coverage Matrix, Policy Fit Simulator, Change Radar, source citations, one secure role-based workflow, one reliable voice brief. |
| Scope lock | One therapeutic area, 4-5 payers, 20-40 public documents, 5-7 drug families, 2-4 version pairs for semantic diff. |
| Compliance | Hackathon build uses no real patient data. Describe it as HIPAA-aware architecture, not as a live HIPAA-compliant deployment. |
| Judge line | Most policy trackers tell you what a document says. PrismRx tells you what it means for access, what changed, and what to do next. |

# 1. Strategy and scope lock

The product should behave like a focused coverage intelligence workspace, not a general-purpose document chat tool. Keep the story simple: compare payers, understand access criteria, simulate a case, and show what changed.

| Product concept | Coverage Matrix for fast plan-by-plan comparison. Policy Fit Simulator to show blockers, missing evidence, and next-best action. Change Radar to detect semantic shifts between policy versions. Evidence Pack with source-backed checklist and short PA summary. |
| --- | --- |
| Primary users | Analyst: compare coverage posture, preferred products, and policy drift. Access coordinator: understand what is missing for a synthetic patient case. Judge view: one clean demo path with visible citations and clear outcomes. |
| Guardrails | Public payer documents only. Synthetic patient scenarios only; no member identifiers, no claims uploads, no PHI. One therapeutic area only: autoimmune / inflammatory infused biologics. One agent orchestrator with tool calls; avoid an overbuilt multi-agent stack. |
| Stretch innovations | Access Friction Score to quantify administrative burden. Impact Replay to show which archetype cases are newly approved or blocked after a policy change. Policy Linter to flag vague, conflicting, or incomplete payer language. Biosimilar Switch Map if core flows ship early. |

Compliance posture for the demo Do not claim HIPAA compliance for the hackathon MVP. Say that the build uses only public policy documents and synthetic cases, while the architecture is designed to be adaptable to a HIPAA-regulated environment later.

| Success test | What the judge should see | Priority |
| --- | --- | --- |
| Coverage query | A drug query instantly shows which plans cover it, under what conditions, with visible citations. | Must |
| Case simulation | A synthetic case reveals blockers, missing evidence, and the fastest likely approvable path. | Must |
| Version change | A quarter-over-quarter view labels a policy as tightened, loosened, or unchanged. | Must |

# 2. 48-hour sprint roadmap

The sprint plan below is optimized for a hackathon team. It front-loads data risk, forces visible milestones by hour 26, and protects demo time at the end.

| S0 | S1 | S2 | S3 | S4 | S5 | S6 | S7 |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Sprint | Hours | Outcome | Gate |
| --- | --- | --- | --- |
| S0 | 0-3 | Lock scope, repo, schema, source manifest, and wireframes. | Start |
| S1 | 3-10 | Capture and parse payer policy documents with source traceability. | h10 |
| S2 | 10-18 | Normalize policies into Policy DNA with drug and code mapping. | h18 |
| S3 | 18-26 | Ship search, Coverage Matrix, and policy detail drawer. | h26 |
| S4 | 26-34 | Ship Policy Fit Simulator and evidence pack. | h34 |
| S5 | 34-40 | Ship Change Radar, semantic diff, and friction score. | h40 |
| S6 | 40-45 | Integrate Auth0 roles and one stable ElevenLabs voice flow. | h45 |
| S7 | 45-48 | QA, backup assets, final demo story, and pitch lock. | Finish |

| Recommended team split Data / policy lead: source manifest, parsing QA, normalization rules. Backend / AI lead: schema, extraction pipeline, tool orchestration, diff logic. Frontend / product lead: search, matrix, simulator, visual polish. Pitch / ops lead: demo story, screenshots, fallback assets, submission. | Checkpoint rules At h10, stop adding sources and make parsing reliable. At h26, matrix must work before simulator complexity grows. At h40, freeze new core features and focus on demo integrity. At h45, record a backup walkthrough and export screenshots. |
| --- | --- |

# 3. Detailed sprint plan | foundation

SPRINT 0 ¦ Scope lock + source manifest ¦ Hours 0-3

| Objective | Eliminate drift before coding starts by freezing the product wedge, data scope, and required screens. |
| --- | --- |
| Key tasks | Freeze one therapeutic area: autoimmune / inflammatory infused biologics. Select 4-5 payers and list 20-40 official public policy documents with effective dates. Define the Policy DNA schema, citation model, and repo structure. Sketch the four core screens: landing, Coverage Matrix, simulator, and Change Radar. |
| Done when | Source manifest exists and every document has a URL, date, and version label. Schema is frozen for the weekend and scope creep is blocked. Every teammate knows the exact demo flow and handoff points. |

Risk note: If data sources look unstable, reduce payer count immediately rather than expanding later.

SPRINT 1 ¦ Capture + parse public policies ¦ Hours 3-10

| Objective | Turn payer PDFs and policy pages into clean text, section boundaries, and source-backed evidence spans. |
| --- | --- |
| Key tasks | Download documents and stamp each with payer, plan type, effective date, and hash. Parse PDF and HTML sources while preserving page numbers or section anchors. Split content into indications, criteria, site of care, renewal, exclusions, and notes. Store raw file, cleaned text, and citation metadata in a repeatable pipeline. |
| Done when | At least 12 high-value documents parse cleanly. Every extracted snippet can point back to its source page or section. The ingestion script can rerun without duplicating records. |

Risk note: Manual curation is allowed; a reliable document set beats a flaky crawler in a hackathon.

# 3. Detailed sprint plan | foundation continued

SPRINT 2 ¦ Normalize into Policy DNA ¦ Hours 10-18

| Objective | Convert messy payer language into structured policy objects that can be compared and queried. |
| --- | --- |
| Key tasks | Map brand and generic names to a canonical drug key using RxNorm. Attach biosimilar and reference-product relationships using the FDA Purple Book. Add HCPCS or J-code context wherever the source policy exposes it. Populate structured fields for coverage status, prior failure, specialist requirement, labs, site of care, and reauthorization. |
| Done when | Every target document produces a Policy DNA JSON object. Drug synonyms resolve across payers without duplicate identities. Structured policy data is queryable in Postgres and ready for the UI layer. |

Risk note: Do not overtrain a model here; rules plus light extraction are enough for the demo.

Minimum Policy DNA fields by the end of Sprint 2

| Field | Why it matters |
| --- | --- |
| Canonical drug key | Unifies brand, generic, and biosimilar references across payer wording. |
| Payer + plan metadata | Makes comparisons meaningful by storing payer, plan type, and effective date. |
| Coverage status | Distinguishes covered, conditional, preferred, nonpreferred, or unclear status. |
| Clinical criteria | Captures prior failure, diagnosis, specialty, and lab requirements. |
| Operational rules | Stores site-of-care, renewal, dosing, or documentation rules when visible. |
| Evidence citations | Keeps every extracted fact tied to a page or section for judge trust. |

Fallback extraction rule If one payer policy resists clean parsing, hand-curate the core fields for the highest-value documents instead of burning hours on perfect automation.

# 4. Detailed sprint plan | user-facing intelligence

SPRINT 3 ¦ Coverage Matrix + search ¦ Hours 18-26

| Objective | Ship the first judge-visible surface: a fast comparison workspace with evidence and effective dates. |
| --- | --- |
| Key tasks | Build a landing page with three paths: Compare a drug, Run a case, See what changed. Build the Coverage Matrix with status badges and quick criteria summaries. Create a policy detail drawer with citations, version metadata, and key criteria chips. Add filters for payer, drug family, preferred product, and restriction type. |
| Done when | A judge can answer 'Which plans cover Drug X?' in one interaction. Every visible answer shows source evidence and effective date. The UI feels premium, clear, and fast enough for live demo use. |

Risk note: If data is sparse, narrow the matrix to the strongest drug families instead of showing weak rows.

SPRINT 4 ¦ Policy Fit Simulator + evidence pack ¦ Hours 26-34

| Objective | Make the product actionable by showing what blocks approval for a synthetic patient case. |
| --- | --- |
| Key tasks | Build a synthetic case form with diagnosis, prior therapies, specialty, setting, age, and labs. Create a rule-based evaluator that compares the case against each Policy DNA object. Surface blockers, missing evidence, preferred alternatives, and likely fit by payer. Generate a short evidence pack with a checklist and a concise PA-ready summary. |
| Done when | At least three synthetic cases run end-to-end without ambiguity. Blockers are explicit and tied back to citations. No real patient or member data enters the system. |

Risk note: Name this feature 'Policy Fit' or 'Access Blockers'; avoid claiming approval prediction.

# 4. Detailed sprint plan | user-facing intelligence continued

SPRINT 5 ¦ Change Radar + friction intelligence ¦ Hours 34-40

| Objective | Show not only what a policy says, but how it changed and how hard access becomes. |
| --- | --- |
| Key tasks | Build a semantic diff that labels criteria as tightened, loosened, or unchanged. Compute an Access Friction Score from burden factors such as prior failure, specialty, labs, site of care, and renewal complexity. Add a simple Impact Replay showing which archetype cases newly pass or fail after a version change. Render one clean heatmap or trend view for presentation value. |
| Done when | At least four policy version pairs can be compared cleanly. One chart or heatmap renders without clutter and supports the story. The team can answer 'What changed this quarter?' with visible proof. |

Risk note: This is the out-of-the-box differentiator. Do not reduce it to a raw text diff.

Keep the friction score simple

| Lever | Example signal | Impact cue |
| --- | --- | --- |
| Prior failure burden | Requires one or more failed therapies first. | High |
| Specialist gate | Must be prescribed by a specialist. | Medium |
| Lab or biomarker gate | Extra testing is required before coverage. | Medium |
| Site-of-care restriction | Hospital infusion is blocked in favor of lower-cost sites. | High |
| Renewal complexity | Short reauthorization interval or extra documentation. | Medium |

Impact Replay seed cases Prepare three synthetic archetypes: a clean approval, a missing-lab case, and a site-of-care restricted case. Replay them across old and new policy versions to show immediate impact.

# 5. Detailed sprint plan | integrations, QA, and demo

SPRINT 6 ¦ Auth0 + ElevenLabs + trust layer ¦ Hours 40-45

| Objective | Use the sponsor integrations in ways that directly support the real workflow. |
| --- | --- |
| Key tasks | Auth0: add login plus role-based views for analyst and access coordinator. Gate sensitive actions such as export, admin review, or internal notes by role. ElevenLabs: ship one stable flow only — a 30-second policy brief or peer-to-peer rehearsal mode. Add clear compliance messaging, minimal event logging, and no PHI-bearing analytics. |
| Done when | Login works and role changes visible behavior in the app. One reliable voice flow speaks a useful summary, not a gimmick. The security story is simple, honest, and easy to explain to judges. |

Risk note: If voice becomes unstable, keep a single pretested summary flow rather than a full spoken agent experience.

SPRINT 7 ¦ Hardening + pitch lock ¦ Hours 45-48

| Objective | Protect the demo by removing failure points and freezing the story. |
| --- | --- |
| Key tasks | Polish loading states, empty states, badge text, and animation timing. Rehearse the 90-second live path and a 3-minute backup version. Capture fallback screenshots, sample outputs, and a screen recording. Stop all feature additions and run a final QA sweep on every route. |
| Done when | Zero broken routes, missing citations, or dead-end UI states. Backup assets are saved locally and ready if Wi-Fi fails. Pitch hits problem, solution, sponsor fit, technical novelty, and future impact. |

Risk note: The last three hours should feel boring. Boring means stable, and stable wins demos.

Contingency tree if the build falls behind If parsing is weak, manually curate the best 12 documents and proceed. If semantic diff slips, ship structured criteria comparisons for two version pairs only. If Auth0 takes too long, keep login and one role-sensitive view. If ElevenLabs is unstable, use one pretested voice brief modal instead of a live conversation.

# 5. Detailed sprint plan | final demo lock

Use the last hours to make the judges feel the product is finished, trustworthy, and easy to understand.

| 90-second demo arc Start with a drug query in the Coverage Matrix. Open one payer policy and show visible source citations. Run a synthetic case and surface blockers plus next-best action. Finish with a quarter-over-quarter change that tightened access. | Submission checklist README explains public-data-only and synthetic-case posture. Screenshots capture matrix, simulator, and change radar. Architecture diagram labels Auth0 and ElevenLabs clearly. Pitch deck repeats the one-sentence wedge consistently. |
| --- | --- |

Pitch spine to rehearse

| 1 | Why this problem matters: coverage rules are fragmented, inconsistent, and slow down access. |
| --- | --- |
| 2 | What PrismRx does: normalize policy language into comparable, queryable Policy DNA. |
| 3 | Show the live demo: matrix, policy detail, synthetic case blocker view, and policy change. |
| 4 | Why the sponsor tools matter: Auth0 secures role-based workflows and ElevenLabs delivers one clear spoken brief. |
| 5 | Future value: more payers, broader therapeutic areas, and production-grade compliance controls later. |

Final reminder Record the backup walkthrough before polishing the last visual details. Stability beats one more unfinished feature.

# 6. Quick reference appendix

These lists make Sprint 0 faster by turning open-ended research into a fixed starting set.

| Data source | Use in PrismRx | Priority |
| --- | --- | --- |
| Aetna medical policy bulletins | Primary public payer policy source for medical-benefit drug criteria and version dates. | Must |
| UnitedHealthcare provider drug policy pages | Public comparison source for specialty injectable / medical benefit rules. | Must |
| Blue Shield of California policy list | Strong public payer source with medication policy detail. | Must |
| Anthem provider policy pages | Additional public payer variation for comparison and drift. | Should |
| Cigna coverage / precertification pages | Secondary payer source if document mix needs more variety. | Should |
| RxNorm | Canonical drug name and synonym normalization. | Must |
| FDA Purple Book | Reference product and biosimilar relationships. | Must |
| CMS HCPCS / J-code files | Billing-code context and code normalization where available. | Must |
| Synthea synthetic records | Synthetic patient-like cases for the simulator and demo. | Must |

| Initial drug family list Must: infliximab family (Remicade, Inflectra, Renflexis, Avsola). Must: rituximab family (Rituxan, Truxima, Ruxience, Riabni). Must: vedolizumab (Entyvio). Must: tocilizumab IV (Actemra). Must: ocrelizumab (Ocrevus). Stretch: abatacept IV (Orencia) and golimumab IV (Simponi Aria). | Stack + UI blueprint Frontend: Next.js, TypeScript, Tailwind, shadcn/ui, Framer Motion. Backend: FastAPI, Pydantic, Postgres, pgvector, object storage. Parsing: PyMuPDF or pdfplumber, BeautifulSoup, Playwright as needed. Auth0 for roles and gated actions; ElevenLabs for one voice brief flow. Visual direction: deep navy, cyan, violet, clinical-trust styling with strong tables. Loading copy: Decomposing payer language... Resolving biosimilar relationships... Computing policy drift... |
| --- | --- |

Final guidance Win by being narrow, explainable, and stable. A working matrix + simulator + change story is better than a giant unfinished feature list. Keep citations visible, use sponsor tools with purpose, and protect the last hours for polish.